AURA EVENTS & CONSULTING

Creating Atmospheres, Not Just Events

Official Event Experience & Operations Consulting Partner

Sales Targets and Performance Plan

Measurable Sales & Revenue Plan – Aura Consulting Fee & Pipeline for FutureFest 2026

Prepared for

FutureFest Pakistan 2026

Pakistan's Largest Tech Festival  |  Expo Center Karachi  |  15,000+ Visitors

Document ID: AURA-PLAN-SAL-01  |  Version 1.0  |  19 October 2026

60-Day Engagement  |  PKR 8,000,000 Event Budget  |  PKR 1,800,000 Consulting Fee

1. Document Control

| Field | Details |
| --- | --- |
| Document ID | AURA-PLAN-SAL-01 |
| Document Title | Sales Targets and Performance Plan |
| Version | 1.0 |
| Effective Date | 19 October 2026 |
| Review Date | 19 April 2027 |
| Owner / Department | Sales & Client Acquisition Manager |
| Status | Active |
| Classification | Internal – Aura × FutureFest Pakistan |
| Related Project | FutureFest Pakistan 2026 – Expo Center Karachi |

2. Purpose

To set clear, measurable sales and performance targets for Aura Events & Consulting during the FutureFest Pakistan 2026 engagement, focusing on the PKR 1,800,000 consulting fee and broader pipeline development.

3. Scope

Sales activities, lead generation, conversion, CRM discipline and KPI tracking for the 60-day engagement and immediate post-event period.

4. Primary Client Revenue – FutureFest Pakistan

| Component | Amount (PKR) | Timing |
| --- | --- | --- |
| Total Consulting Fee | 1,800,000 | Full engagement |
| Advance (40%) | 720,000 | On contract signing |
| Pre-Event (30%) | 540,000 | 15 days before event |
| Final (30%) | 540,000 | After final report submission |

5. Monthly / Quarterly Targets (Assumptions)

Assumptions: Primary revenue from FutureFest fee; secondary pipeline from exposure at the festival.

| Period | Revenue Target (PKR) | Focus |
| --- | --- | --- |
| Month 1 (Planning) | 1,200,000 | Secure advance + early pipeline |
| Month 2 (Pre-Event) | 1,800,000 | Full fee recognition + additional leads |
| Month 3 (Post-Event) | 1,500,000 | Final payment + new client conversion |

6. Lead Pipeline & Conversion

•  Target pipeline: 20 inquiries → 8 qualified meetings → 4 closed deals = 20% overall conversion.

•  Lead sources (indicative mix): FutureFest exposure 40% | Instagram 30% | Referrals 20% | Expo / other referrals 10%.

7. Key Performance Indicators (KPIs)

| KPI | Target | Measurement |
| --- | --- | --- |
| Lead Generation | 30 qualified leads / month | CRM / Sales Tracker |
| Conversion Rate | ≥ 20% | Closed / Qualified Meetings |
| NPS – FutureFest Committee | > 8.5 / 10 | Post-engagement survey |
| On-time Delivery | ≥ 95% | Milestone checklist |
| Budget Variance (managed PKR 8M) | < 5% | Finance reports |
| Crowd Satisfaction (15k visitors) | > 4.5 / 5 | QR feedback survey |

8. CRM & Follow-up Procedure

•  All leads logged in Sales Tracker (Excel / approved CRM).

•  Follow-up cadence: Day 1 (email), Day 3 (call), Day 7 (final call / decision).

•  Proposal standard: 3-tier (Basic 6M / Premium 8M / Elite 10M) delivered within 48 hours of needs assessment.

9. Performance Review & Improvement

•  Weekly sales pipeline review with Sales Manager and CEO.

•  Monthly formal performance review against KPIs.

•  Missed targets trigger documented improvement plan with clear actions and support.

Compliance & Approval

This document forms part of the official Aura Events & Consulting operating system for the FutureFest Pakistan 2026 engagement. All team members and authorised volunteers must comply with the procedures herein. Non-compliance may result in disciplinary action or removal from the project.

| Role | Name / Position | Signature | Date |
| --- | --- | --- | --- |
| Prepared by | Documentation & Compliance Coordinator |  | 19 Oct 2026 |
| Reviewed by | Operations Manager |  | 19 Oct 2026 |
| Approved by | CEO / Founder – Aura Events & Consulting |  | 19 Oct 2026 |
| Client Acknowledgement | FutureFest Pakistan Committee |  |  |

Note: These are project deliverables prepared for academic / simulation purposes. A real business owner and qualified advisers should review and approve policies before implementation, especially where employment, privacy, finance, safety or other legal requirements apply under Pakistani law.