AURA EVENTS & CONSULTING

Creating Atmospheres, Not Just Events

Official Event Experience & Operations Consulting Partner

Finance and Expense Management SOP

Budget Control, Approvals & Financial Controls for PKR 8,000,000 Event Budget

Prepared for

FutureFest Pakistan 2026

Pakistan's Largest Tech Festival  |  Expo Center Karachi  |  15,000+ Visitors

Document ID: AURA-SOP-FIN-01  |  Version 1.0  |  19 October 2026

60-Day Engagement  |  PKR 8,000,000 Event Budget  |  PKR 1,800,000 Consulting Fee

1. Document Control

| Field | Details |
| --- | --- |
| Document ID | AURA-SOP-FIN-01 |
| Document Title | Finance and Expense Management SOP |
| Version | 1.0 |
| Effective Date | 19 October 2026 |
| Review Date | 19 April 2027 |
| Owner / Department | Finance & Budget Manager |
| Status | Active |
| Classification | Internal – Aura × FutureFest Pakistan |
| Related Project | FutureFest Pakistan 2026 – Expo Center Karachi |

2. Purpose

To establish transparent financial controls, approval hierarchies and record-keeping for the PKR 8,000,000 FutureFest Pakistan 2026 event budget managed by Aura Events & Consulting, and for Aura’s own consulting fee of PKR 1,800,000.

3. Scope

All budgeting, expense approval, vendor payments, petty cash, invoicing, reconciliation and fraud-prevention activities related to the FutureFest engagement.

4. Event Budget Breakdown (PKR 8,000,000)

| Category | Amount (PKR) | % of Total |
| --- | --- | --- |
| Venue – Expo Center Karachi | 2,000,000 | 25% |
| AV & Lighting | 1,500,000 | 18.75% |
| Security & Crowd Management | 800,000 | 10% |
| Decor & Branding | 1,000,000 | 12.5% |
| Catering (Staff / VIP) | 700,000 | 8.75% |
| Marketing & Ticketing | 500,000 | 6.25% |
| Contingency (10%) | 500,000 | 6.25% |
| Other / Buffer & Coordination | 1,000,000 | 12.5% |
| TOTAL EVENT BUDGET | 8,000,000 | 100% |

Aura Consulting Fee (PKR 1,800,000) is separate and invoiced according to the 40% / 30% / 30% schedule.

5. Three-Tier Proposal Structure

| Tier | Budget (PKR) | Key Differentiator |
| --- | --- | --- |
| Basic | 6,000,000 | Essential delivery |
| Premium (Recommended) | 8,000,000 | Full scope + contingency |
| Elite | 10,000,000 | Premium + extra LED wall & enhanced production |

6. Expense Approval Limits

| Amount (PKR) | Approver |
| --- | --- |
| Up to 50,000 | Lead Event Planner |
| 50,001 – 200,000 | Operations Manager |
| Above 200,000 | CEO + FutureFest Committee (as required) |

7. Petty Cash & On-site Expenses

•  Petty cash float: PKR 20,000 at Expo Center for urgent small expenses.

•  All petty cash spends accounted for with receipts within 24 hours.

8. Vendor Payment Terms

•  Standard: 30% advance | 40% one day before delivery / event | 30% after satisfactory completion.

•  Payment by bank transfer only against original invoice.

•  No cash payments above PKR 20,000.

9. Fraud Prevention & Controls

•  Two signatures required for any payment above PKR 100,000.

•  Monthly reconciliation by Finance Manager.

•  Full audit of event expenditure after FutureFest close.

•  Conflicts of interest must be declared; no self-dealing with vendors.

Compliance & Approval

This document forms part of the official Aura Events & Consulting operating system for the FutureFest Pakistan 2026 engagement. All team members and authorised volunteers must comply with the procedures herein. Non-compliance may result in disciplinary action or removal from the project.

| Role | Name / Position | Signature | Date |
| --- | --- | --- | --- |
| Prepared by | Documentation & Compliance Coordinator |  | 19 Oct 2026 |
| Reviewed by | Operations Manager |  | 19 Oct 2026 |
| Approved by | CEO / Founder – Aura Events & Consulting |  | 19 Oct 2026 |
| Client Acknowledgement | FutureFest Pakistan Committee |  |  |

Note: These are project deliverables prepared for academic / simulation purposes. A real business owner and qualified advisers should review and approve policies before implementation, especially where employment, privacy, finance, safety or other legal requirements apply under Pakistani law.