AURA EVENTS & CONSULTING

Creating Atmospheres, Not Just Events

Official Event Experience & Operations Consulting Partner

Operations and Quality Control SOP

End-to-End Workflow, Daily Task Allocation & Quality Checkpoints for FutureFest 2026

Prepared for

FutureFest Pakistan 2026

Pakistan's Largest Tech Festival  |  Expo Center Karachi  |  15,000+ Visitors

Document ID: AURA-SOP-OPS-01  |  Version 1.0  |  19 October 2026

60-Day Engagement  |  PKR 8,000,000 Event Budget  |  PKR 1,800,000 Consulting Fee

1. Document Control

| Field | Details |
| --- | --- |
| Document ID | AURA-SOP-OPS-01 |
| Document Title | Operations and Quality Control SOP |
| Version | 1.0 |
| Effective Date | 19 October 2026 |
| Review Date | 19 April 2027 |
| Owner / Department | Operations Manager |
| Status | Active |
| Classification | Internal – Aura × FutureFest Pakistan |
| Related Project | FutureFest Pakistan 2026 – Expo Center Karachi |

2. Purpose

To define the standard operating workflow, daily task allocation and quality assurance checkpoints that ensure successful delivery of FutureFest Pakistan 2026 for 15,000+ visitors at Expo Center Karachi.

3. Scope

All operational activities from initial inquiry through post-event reporting for the Aura × FutureFest engagement.

4. End-to-End Process

1.  Inquiry received from FutureFest Committee.

2.  Site visit at Expo Center – measure halls, exits, power points.

3.  Three-tier budget proposal prepared.

4.  Vendor booking (AV, security, décor) from 100+ verified Karachi vendor list.

5.  Design approval – stall layout (2D CAD), branding mock-ups.

6.  Rehearsal / dry run one day before with FutureFest team.

7.  Execution – 3 event days.

8.  Feedback (NPS / QR survey to visitors) and final report.

5. Daily Task Allocation (Event Days)

Day 1 – Setup

•  Ops Manager + Lead Planner + 20 volunteers: stall marking, AV setup, branding installation.

Day 2 & 3 – Live Event

•  All 11 core members + 50 volunteers deployed as:

| Zone | Headcount (indicative) |
| --- | --- |
| Registration / QR Scan | 6 |
| Crowd Flow Management | 10 |
| Stall Support | 10 |
| VIP Lounge | 5 |
| Command Center (Hall 2) | 2 |
| Roaming / Floater | Remainder |

Daily Operations Report submitted by Ops Manager by 7:00 PM to FutureFest Committee.

6. Quality Checkpoints

•  Sound check completed 2 hours before gates open.

•  Catering buffer: +10% (approx. 16,500 covers planned for 15,000 visitors).

•  Backup power: generator on standby; AV on UPS (10-minute switchover).

•  Security headcount / status check every 2 hours.

•  Stall readiness verified before public entry.

7. Handling Delays & Issues

•  Any delay or quality deviation logged and escalated immediately to Ops Manager.

•  Corrective action recorded; preventive measures added to post-event review.

Compliance & Approval

This document forms part of the official Aura Events & Consulting operating system for the FutureFest Pakistan 2026 engagement. All team members and authorised volunteers must comply with the procedures herein. Non-compliance may result in disciplinary action or removal from the project.

| Role | Name / Position | Signature | Date |
| --- | --- | --- | --- |
| Prepared by | Documentation & Compliance Coordinator |  | 19 Oct 2026 |
| Reviewed by | Operations Manager |  | 19 Oct 2026 |
| Approved by | CEO / Founder – Aura Events & Consulting |  | 19 Oct 2026 |
| Client Acknowledgement | FutureFest Pakistan Committee |  |  |

Note: These are project deliverables prepared for academic / simulation purposes. A real business owner and qualified advisers should review and approve policies before implementation, especially where employment, privacy, finance, safety or other legal requirements apply under Pakistani law.