AURA EVENTS & CONSULTING

Creating Atmospheres, Not Just Events

Official Event Experience & Operations Consulting Partner

Business Continuity and Incident Response Plan

Maintaining FutureFest 2026 Operations Despite Disruptions

Prepared for

FutureFest Pakistan 2026

Pakistan's Largest Tech Festival  |  Expo Center Karachi  |  15,000+ Visitors

Document ID: AURA-PLAN-BCP-01  |  Version 1.0  |  19 October 2026

60-Day Engagement  |  PKR 8,000,000 Event Budget  |  PKR 1,800,000 Consulting Fee

1. Document Control

| Field | Details |
| --- | --- |
| Document ID | AURA-PLAN-BCP-01 |
| Document Title | Business Continuity and Incident Response Plan |
| Version | 1.0 |
| Effective Date | 19 October 2026 |
| Review Date | 19 April 2027 |
| Owner / Department | Operations Manager / IT & Systems Manager |
| Status | Active |
| Classification | Internal – Aura × FutureFest Pakistan |
| Related Project | FutureFest Pakistan 2026 – Expo Center Karachi |

2. Purpose

To ensure that essential activities of FutureFest Pakistan 2026 can continue or be rapidly restored in the event of IT outages, vendor failures, personnel absences, crowd emergencies, power failure or other disruptions.

3. Scope

All continuity and incident-response procedures applicable to the Aura-managed elements of FutureFest 2026 at Expo Center Karachi.

4. Key Scenarios & Responses

4.1 IT Outage – Ticketing System Down

•  Backup: Printed manual QR / attendee list prepared 1 day before.

•  Offline Excel registers at 6 desks for manual entry.

•  IT Manager target resolution: within 1 hour.

•  Communication via radio / designated runners if network fails.

4.2 Vendor Cancellation (Last-Minute)

•  Pre-negotiated backup vendor list (minimum 3 vendors per critical category) at up to 20% premium.

•  Switch authorised by CEO; target activation within 2 hours.

4.3 Unexpected Key Absence

•  Ops Manager unavailable → Lead Event Planner assumes command; CEO on-site delegation chart activated.

•  Other key roles have named deputies.

4.4 Crowd Emergency / Fire / Panic

•  Evacuation via 4 marked exits to Assembly Point – Parking B.

•  2 ambulances on-site; fire extinguishers in each hall.

•  Pre-approved announcement script used.

•  Incident Report completed within 2 hours.

4.5 Power Failure

•  Backup generators: 2 × 100 kVA pre-booked.

•  Critical AV on UPS with 10-minute switchover window.

4.6 Sponsor / Branding Complaint

•  Immediate assessment and fix target: within 1 hour.

•  Apology and compensatory action (e.g., extra visibility slot) as appropriate.

5. Emergency Contact Tree

| Level | Role / Service | Contact |
| --- | --- | --- |
| 1 | Operations Manager | +92 300 1111111 |
| 2 | CEO / Founder | +92 300 2222222 |
| 3 | Expo Center Security | +92 21 1111111 |
| 4 | Edhi Ambulance | 115 |
| 5 | Fire Brigade | 16 |

6. Recovery Priorities

1.  Life safety and medical response.

2.  Crowd control and evacuation if required.

3.  Restoration of ticketing / access control.

4.  Critical AV and stage functionality.

5.  Full operational recovery and stakeholder communication.

Compliance & Approval

This document forms part of the official Aura Events & Consulting operating system for the FutureFest Pakistan 2026 engagement. All team members and authorised volunteers must comply with the procedures herein. Non-compliance may result in disciplinary action or removal from the project.

| Role | Name / Position | Signature | Date |
| --- | --- | --- | --- |
| Prepared by | Documentation & Compliance Coordinator |  | 19 Oct 2026 |
| Reviewed by | Operations Manager |  | 19 Oct 2026 |
| Approved by | CEO / Founder – Aura Events & Consulting |  | 19 Oct 2026 |
| Client Acknowledgement | FutureFest Pakistan Committee |  |  |

Note: These are project deliverables prepared for academic / simulation purposes. A real business owner and qualified advisers should review and approve policies before implementation, especially where employment, privacy, finance, safety or other legal requirements apply under Pakistani law.